## Sheet1
Use Case Level Activity
Activity Category | Low Level Activities | W1 | W2 | W3 | W4 | W5
Due Diligence/Solution Architecture | Due Diligence
Design & Arch
Code Quality Assessment | Identify all the avilable data sources
Extract data from data sources and centralize it
Pre Process health report data based on each patient profile
Chunking and indexing patient profiles
Generate Embedding and vector DB based on each patient profile
Use Agentic RAG for faster query context
Code Optimization | Grab all the health check up reports for each patient
Club all the health reports with patient ID to maintain Json profile
Create vector DB with patient id index
Use RAG to identifying on going treatment
Similarity search to gather contextual data for each profile
Prompt engineerig to generare recommendation for each profile
Auto Code Documentation | Testing (UC1)
Testing (UC2)
Testing (MFT+ Integration)
Overall Testing
Code Reframing
Summary timeline for Use Case Level Activity
Activity Category | High Level Activities | W1 | W2 | W3 | W4 | W5
Due Diligence/Solution Architecture | Due Diligence
Design & Arch
Dev (UC1) | UC1 Development
Dev (UC2) | UC2 Development
Testing | Test Strategy & Planning
Test Case Generation
Testing
Testing (MFT+ Integration)
Overall Testing